## Sheet1
Req ID | Name | Priority | Sprint | Hours | Completed
1 | Start Recording | 1 | 1 | 1 | Yes
2 | Pause Recording | 2 | 1 | 5 | Yes
3 | Stop Recording | 1 | 1 | 1 | Yes
4 | Save Recording | 1 | 1 | 3 | Yes
6 | View Recording | 1 | 1 | 4 | Yes
7 | Play | 1 | 1 | 2 | Yes
8 | Pause | 2 | 1 | 4 | Yes
9 | Stop | 1 | 1 | 1
14 | Open Settings | 1 | 1 | 2 | Yes
17 | Set Max Time | 1 | 1 | 2 | 90%
18 | Create GUI | 1 | 1 | 20 | Yes
21 | Search | 1 | 1 | 3
5 | Delete Recording | 2 | 2 | 2 | Yes
10 | Rename Recording | 2 | 2 | 2 | Yes
11 | Share Recording | 2 | 2 | 2
12 | Restore Recording | 3 | 2 | 4
13 | Backup Recordings | 3 | 2 | 4
15 | Change Quality | 2 | 2 | 2 | 20%
16 | Change Codec | 2 | 2 | 10 | 50%
19 | Create Timer | 2 | 2 | 5
20 | Change View | 3 | 2 | 10
22 | MediaStore | 2 | 2 | 6