## Sheet1
Req ID | Name | Priority | Sprint | Hours | Completed
1 | Start Recording | 1 | 1 | 1 | Yes
2 | Pause Recording | 2 | 1 | 5 | AMR
3 | Stop Recording | 1 | 1 | 1 | Yes
4 | Save Recording | 1 | 1 | 3 | Yes
5 | Delete Recording | 2 | 2 | 2 | Yes
6 | View Recording | 1 | 1 | 4 | Yes
7 | Play | 1 | 1 | 2 | 60%
8 | Pause | 2 | 1 | 4 | 60%
9 | Stop | 1 | 1 | 1 | 60%
10 | Rename Recording | 2 | 2 | 2 | 90%
11 | Share Recording | 2 | 2 | 2
12 | Restore Recording | 3 | 2 | 4
13 | Backup Recordings | 3 | 2 | 4
14 | Open Settings | 1 | 1 | 2
15 | Change Quality | 2 | 2 | 2
16 | Change Codec | 2 | 2 | 2
17 | Set Max Time | 1 | 1 | 2
18 | Create GUI | 1 | 1 | 20 | Yes
19 | Create Timer | 2 | 2 | 5